## Sheet1
SPRINT #2 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
10 | As a customer, I want to be able to book a specific service, date and worker so that I am guaranteed the time, service and worker | 10.2 | -Create basic structure of booking page | Kajal |  |  | ✓
|  | 10.3 | - Implement booking functionality | Luke |  |  | ✓
|  | 10.4 | - Test the bookings form | Kajal |  |  | ✓
|  | 10.5 | - Integrate the bookings form | Luke |  |  | ✓
2 | As a worker i would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | 2.2 | - Validate usernames/passwords | Kevin |  |  | ✓
|  | 2.3 | - Allow access to logged in state of homepage | Cass |  |  | ✓
|  | 2.4 | - Test worker login | Chris |  |  | ✓
|  | 2.5 | - Integrate backend-frontend for worker login | Cass |  |  | ✓
3 | As a customer would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | 3.2 | - Validate usernames/passwords | Kevin |  |  | ✓
|  | 3.3 | - Allow access to logged in state of homepage | Cass |  |  | ✓
|  | 3.4 | - Test customer login | Chris |  |  | ✓
|  | 3.5 | - Integrate backend-frontend for cust. login | Cass |  |  | ✓
9 | As an Admin, I want to be able to login, So that I can perform administrative functions | 9.2 | -Validate usernames/passwords | Kevin |  | ✓
|  | 9.3 | - Allow access to logged in state of homepage | Cass |  | ✓
|  | 9.4 | - Test admin login | Chris |  | ✓
|  | 9.5 | - Integrate backend-frontend for admin login | Cass |  | ✓
5 | As a customer, I want to register an account so that I can easily book an appointment online | 5.1 | -Create sign up form | Kevin |  |  | ✓
|  | 5.2 | -Add new account to account storage | Cass |  |  | ✓
|  | 5.3 | - Test customer sign-up | Chris |  |  | ✓
|  | 5.4 | - Integrate backend-frontend for cust. sign-up | Luke |  |  | ✓
18 | As a customer i want to be able to see the history of my past bookings so i can keep track of the number of bookings I have made in the past | 18.1 | - Create history page | Kajal |  |  | ✓
|  | 18.2 | - Display previous bookings | Cass |  |  | ✓
|  | 18.3 | - Test bookings history | Kevin |  |  | ✓
|  | 18.4 | - Integrated | Cass |  |  | ✓