## Product Backlog
SPRINT #1 BACKLOG
PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PROGRESS | COMPLETED | NOTES
1 | As a customer who is unfamiliar with technology, I would like to be able to find help easily from the homepage, so that I can book an appointment quickly. | 1.1 | - Create the landing page, to provide a quick access to login | Kevin |  |  | ✓
|  | 1.2 | - Set up SprintBoot | Luke |  |  | ✓
|  | 1.3 | - Set up React | Kajal |  |  | ✓
|  | 1.4 | - Set up Git Deployment | Luke |  |  | ✓
2 | As a worker i would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | 2.1 | - Define worker api | Luke |  | ✓
|  | 2.2 | - Validate usernames/passwords | Chris |  | ✓
|  | 2.3 | - Check if it is a customer account, admin or worker account | Cass |  | ✓
|  | 2.4 | - Display worker only page | Kevin |  | ✓
3 | As a customer would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | 3.1 | - Define customer api | Luke |  | ✓
|  | 3.2 | - Validate usernames/passwords | Chris |  | ✓
|  | 3.3 | - Check if it is a customer account, admin or worker account | Cass |  | ✓
|  | 3.4 | - Display customer only page | Kevin |  | ✓
9 | As an Admin, I want to be able to login, So that I can perform administrative functions | 9.1 | - Define admin api | Luke |  | ✓
|  | 9.2 | - Validate usernames/passwords | Chris |  | ✓
|  | 9.3 | - Check if it is a customer account, admin or worker account | Cass |  | ✓
|  | 9.4 | - Display admin only page | Kevin |  | ✓
10 | As a customer, I want to be able to book a specific service, date and worker so that I am guaranteed the time, service and worker | 10.1 | - Create bookings API | Luke |  | ✓
|  | 10.2 | - Create bookings page | Kajal

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 |  | #N/A | #N/A | #N/A | #N/A | #N/A
3 |  | #N/A | #N/A | #N/A | #N/A | #N/A
4 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
5 | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR! | #ERROR!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 |  | #N/A | #N/A | #N/A | #N/A | #N/A
9 |  | #N/A | #N/A | #N/A | #N/A | #N/A
10 |  | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As a customer would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
12 |  | #N/A | #N/A | #N/A | #N/A | #N/A
13 |  | #N/A | #N/A | #N/A | #N/A | #N/A
14 |  | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As an Admin, I want to be able to login, So that I can perform administrative functions | #N/A | #N/A | #N/A | #N/A | #N/A
16 |  | #N/A | #N/A | #N/A | #N/A | #N/A
17 |  | #N/A | #N/A | #N/A | #N/A | #N/A
18 |  | #N/A | #N/A | #N/A | #N/A | #N/A
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | As a customer, I want to be able to book a specific service, date and worker so that I am guaranteed the time, service and worker | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A