## Product Backlog
PRODUCT BACKLOG
ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
1 | As a customer who is unfamiliar with technology, I would like to be able to find help easily from the homepage, so that I can book an appointment quickly. | Chris | 1 | 8 | Completed in Sprint 1 | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
2 | As a worker i would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | Chris | 1 | 8 | Completed in Sprint 2 | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
3 | As a customer would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | Chris | 4 | 5 | Completed in Sprint 2 | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
4 | As a customer, I want to filter a specific service I need and see their available times so that I can plan my bookings | Kevin | 2 | 13 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
5 | As a customer, I want to register an account so that I can easily book an appointment online | Kevin | 1 | 8 | Completed in sprint 2 | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
6 | As a customer, I want to receive updates through my website inbox when I book an appointment so I can be notifed of any changes | Kevin | 3 | 8 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
7 | As an Admin, I want to be able to login, So that I can perform administrative functions | Cass | 1 | 5 | To be completed in Sprint 3 | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
8 | As an Admin, I want to approve new worker accounts, So that I can increase the amount of services provided | Cass | 3 | 8 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
9 | As an Admin, I want to edit an worker, So that I can update any changes to the service provided | Cass | 2 | 5 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
10 | As an Admin, I want to be able to add working times and dates for the next month, So that the calendar for the next month is upto date for any customer bookings | Cass | 2 | 8 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
11 | As an Admin, I want to be able to edit working times and dates for the next month, So that the calendar for the next month is upto date for any customer bookings | Cass | 3 | 5 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
12 | As a customer, I want to be able to check for the availabilities, services and the workers, so I know what time, service and worker will be suitable for me | Kajal | 3 | 3 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
13 | As a customer, I want to be able to book a specific service, date and worker so that I am guaranteed the time, service and worker | Kajal | 1 | 5 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
14 | As a customer, I want to be able to view my details, so that I can confirm that they are correct | Cass | 4 | 3 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
15 | As a customer, I want to be able to edit my details, so that I can keep them up to date or fix any mistakes | Cass | 4 | 3 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
16 | As a customer, I want to be able to cancel my booking if required so that I can notify the business and avoid being charged if I am unable to attend. | Luke | 2 | 8 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
17 | As a worker, I want the check if any appointments have been canceled so that I can plan my work and maximise my time. | Luke | 3 | 5 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
18 | As a customer, I want to be able to see the history of my bookings so I can keep track of the number of bookings I have made in the past | Kajal | 2 | 5 | Completed in Sprint 2 | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
19 | As a worker, i would like to see my profile, so that i can know when i have to work | Chris | 1 | 8 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
20 | As a customer, i would like to see a worker’s profile, so that i know when i am able to book them for a service | Chris | 2 | 5 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
21 | As an Admin I want to view past bookings so that I can review the business’ performance. | Luke | 3 | 3 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
22 | As an Admin I want to view all upcoming bookings so that I can ensure business is continuing to perform well. | Luke | 3 | 8 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
23 | As an Admin I want to view the availability of all works so that I can manage my staff and ensure everyone is working as effectively as possible. | Luke | 3 | 13 | To be completed in future sprint | Functional testing ¦ Unit testing ¦ Code reviewed ¦ Assumptions of User Story met ¦ Refactoring completed
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Calculations (hidden)
This worksheet is used for the Financial Report calculations and should remain hidden.
Position
| This year | #REF! | #NAME?
| Previous Year | #REF! | #NAME?
| Position | #NAME? | #NAME? | #NAME? | #NAME? | #NAME?
| Key Metrics | #REF! | #REF! | #REF! | #REF! | #REF!
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
#REF! | #REF! | #N/A | #N/A | #N/A | #N/A | #N/A
All Metrics (works up to 25 metrics)
1 | As a customer who is unfamiliar with technology, I would like to be able to find help easily from the homepage, so that I can book an appointment quickly. | #N/A | #N/A | #N/A | #N/A | #N/A
2 | As a worker i would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
3 | As a customer would like to be able to login as a worker from the homepage, so that i can quickly access my dashboard | #N/A | #N/A | #N/A | #N/A | #N/A
4 | As a customer, I want to filter a specific service I need and see their available times so that I can plan my bookings | #N/A | #N/A | #N/A | #N/A | #N/A
5 | As a customer, I want to register an account so that I can easily book an appointment online | #N/A | #N/A | #N/A | #N/A | #N/A
6 | As a customer, I want to receive updates through my website inbox when I book an appointment so I can be notifed of any changes | #N/A | #N/A | #N/A | #N/A | #N/A
7 | As an Admin, I want to be able to login, So that I can perform administrative functions | #N/A | #N/A | #N/A | #N/A | #N/A
8 | As an Admin, I want to approve new worker accounts, So that I can increase the amount of services provided | #N/A | #N/A | #N/A | #N/A | #N/A
9 | As an Admin, I want to edit an worker, So that I can update any changes to the service provided | #N/A | #N/A | #N/A | #N/A | #N/A
10 | As an Admin, I want to be able to add working times and dates for the next month, So that the calendar for the next month is upto date for any customer bookings | #N/A | #N/A | #N/A | #N/A | #N/A
11 | As an Admin, I want to be able to edit working times and dates for the next month, So that the calendar for the next month is upto date for any customer bookings | #N/A | #N/A | #N/A | #N/A | #N/A
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | As a customer, I want to be able to book a specific service, date and worker so that I am guaranteed the time, service and worker | #N/A | #N/A | #N/A | #N/A | #N/A
14 | As a customer, I want to be able to view my details, so that I can confirm that they are correct | #N/A | #N/A | #N/A | #N/A | #N/A
15 | As a customer, I want to be able to edit my details, so that I can keep them up to date or fix any mistakes | #N/A | #N/A | #N/A | #N/A | #N/A
16 | As a customer, I want to be able to cancel my booking if required so that I can notify the business and avoid being charged if I am unable to attend. | #N/A | #N/A | #N/A | #N/A | #N/A
17 | As a worker, I want the check if any appointments have been canceled so that I can plan my work and maximise my time. | #N/A | #N/A | #N/A | #N/A | #N/A
18 | As a customer, I want to be able to see the history of my bookings so I can keep track of the number of bookings I have made in the past | #N/A | #N/A | #N/A | #N/A | #N/A
19 | As a worker, i would like to see my profile, so that i can know when i have to work | #N/A | #N/A | #N/A | #N/A | #N/A
20 | As a customer, i would like to see a worker’s profile, so that i know when i am able to book them for a service | #N/A | #N/A | #N/A | #N/A | #N/A
21 | As an Admin I want to view past bookings so that I can review the business’ performance. | #N/A | #N/A | #N/A | #N/A | #N/A
22 | As an Admin I want to view all upcoming bookings so that I can ensure business is continuing to perform well. | #N/A | #N/A | #N/A | #N/A | #N/A
23 | As an Admin I want to view the availability of all works so that I can manage my staff and ensure everyone is working as effectively as possible. | #N/A | #N/A | #N/A | #N/A | #N/A
24 |  | #N/A | #N/A | #N/A | #N/A | #N/A
25 |  | #N/A | #N/A | #N/A | #N/A | #N/A